## Review
Project Code | Group 2 | Review Date | 2017-04-10 | Defect Classification |  | Author | Group 2
Project Name | Asset Management System | Iteration |  | S1 | 6 | Reviewer | Suraj |  |  | Code
Item Name | Code | Time Taken (mts) |  | S2 | 2 | Approver |  |  |  | Document
Config ID |  | Version No. | 1 | S3 | 1 | Status
|  | FDA related requirements checked? | Yes | SG | #REF!
|  |  |  | Total | 9
Asset Management System
Ref No. | Observation | Primary Cause | Origin | Severity | Priority | Defect Type | Action Plan | Status | Planned Closure Date (DD-MMM-YY) | Actual Closure Date (DD-MMM-YY)
Admin Home Page | Improper Alignment | Inadequate Skills | Code | S2 | Meduim | User Interface | Modify and implement CSS. | Closed | 2017-04-10 | 2017-04-10
Asset Not Inserting Into Database | Incomplete Code Written | Inadequate Skills | Code | S2 | High | Functionality | Review Code And Solve Error | Closed | 2017-04-07 | 2017-04-08
Modify Not Able To Populate Values | Defect In code | Inadequate Skills | Code | S1 | High | Functionality | Review Code And Solve Error | Closed | 2017-04-08 | 2017-04-08
Could Not Set the status in database as "AVAILABLE" | Incomplete Code Written | Inadequate Skills | Code | S2 | High | Functionality | Review Code And Solve Error | Closed | 2017-04-08 | 2017-04-08
Review
Test
Note on E9: Total of S1, S2 & S3. 'SG' which stands for Suggestion not included in the Total Defects.

## Sheet2
Guidelines for Defect Type Classification
Defect Type | Description
Functionality | When there is a gap in translating the business requirements to technical specification
When code fails to perform the functionality or abends
Logic related, Misunderstanding of specs, Incomplete coding
Maintainability | Defects related to coding standards, guidelines, naming conventions, comments, No Proper packaging of modules/programs
Documentation | All defects related to documentation like user manual, LUT, Design, etc., incorrect header documentation, insufficient / incorrect comments,
Missing design or Test cases | Gap in understanding, Missed to translate some specs down the line to design, LLD, etc. Expected result of test case is incorrect
Performance | Defects pertaining to performance like cycle time, Speed of loading.
User Interface | UI related defects
Clarity Missing | Pertaining to technical documents like Test Plan, Input documents, Logic Clarity missing
Redundancy | Redundant Code being used, Hard Coding, unwanted alert messages, Unwanted global variables/ import statements
Guidelines for Causal Code Classification
Causal Code | Description
Lack of Communication | Defects due to miscommunication, wrong interpretation of client clarification
Inadequate Skills | Insufficient Training/ Education, Technical insufficiency, Inadequate Domain Knowledge,
Lack of clarity on documentation | Logic clarity missing in Test Cases, Design document, LUT, etc.
.NON Adherence | Did not follow Process, Standards, Guidelines, Templates
Incomplete documentation | All documentation related
Data Error | Data not available, Wrong data Initialization, Data Mismatch, Data not properly defined/dimensioned, Data referenced out-of-bounds, Data written to wrong file/location, Incorrect data format
Guidelines for Severity Classification
Scenario | Design
Requirement (stated & unstated) not handled | S1
Incomplete/incorrect logic | S1
When any of the impacted items are missed out. | S1
Missing out identification of Action entries | S1
Missing out Stored Procedures used | S1
Traceability Matrix is incomplete or absent | S1
Algorithm is not optimized | S2
Validation missed out | S2
Missing out/Wrong Data Mapping entries | S2
Unwanted Session Variables identified. | S2
Standards / Checklists not followed | S3
Typographical Errors | S3
Cosmetic defect | S3
Defect on look and feel of the application | S3
Scenario | Code
Functionality incorrect | S1
Functionality not handled | S1
When any validation gets missed out | S1
Wrong Algorithm | S1
Algorithm is not optimized | S2
Improper use of resources like Connection, Statement and ResultSet etc. | S2
Unwanted Session Variables identified | S2
Cosmetic defect | S3
Data Formatting issues in the screen | S3
Incorrect /incomplete comments | S3
Standards / Checklists not followed | S3
Scenario | Test Plan
Incorrect / Incomplete test case | S1
Test data incorrect | S1
Expected Results incorrect | S1
Incorrect Test Environment Specified | S1
Standards / Checklists not followed | S3
Typographical Errors | S3
Scenario | Testing
Causes Application crash | S1
Functionality not handled/incorrect functionality | S1
Expected Results incorrect | S2
When any validation gets missed out | S2
Defect on look and feel of the application/ Typographical | S3
Scenario | Other Work products
Section completely missed out, no reasons mentioned | S1
Incomplete/Incorrect details | S2
Standards / Checklists not followed | S3
Typographical Errors | S3
`